## Timeline
Task | Start Date | End Date | Status
Find Location | 2026-05-02 | 2026-05-08 | Complete
Order Equipment | 2026-05-07 | 2026-05-14 | In Progress
Hire Staff | 2026-05-10 | 2026-05-20 | Not Started
Marketing Campaign | 2026-05-16 | 2026-05-25 | Not Started
Launch Day | 2026-05-28 | 2026-05-28 | Not Started

## Budget
Expense | Estimated Cost
Rent | 4000
Coffee Equipment | 5000
Furniture | 1200
Marketing | 1300
Staff Wages | 3000
Total Estimated Cost | 14500

## Risks
Risk | Impact | Solution
Supplier Delays | Launch delayed | Order early
Budget Overrun | Higher cost | Track spending weekly
Low Customer Turnout | Low sales | Increase marketing

## Stakeholders
Stakeholder | Role
Owner | Project sponsor
Suppliers | Provide equipment
Employees | Operate coffee shop
Customers | Purchase products